## Project Planner
Project Plan
| Legend for chart is as follows: | [8 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | % Complete (beyond plan)
TIMELINE (BY DAYS IN MONTH OF FEBRUARY)
| ACTIVITY | PLAN START DAY | PLANNED DAYS NEEDED | ACTUAL START DAY | ACTUAL DAYS NEEDED | PERCENT COMPLETE | Inception |  |  |  | Elaboration | [6 empty] | Construction |  |  |  |  | Transition
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
| Setup of TortoiseSVN | 2 | 1 | 2 | 1 | 100%
| Business Use Case | 1 | 1 | 1 | 1 | 100%
| SRS Section 1 -2 | 2 | 2 | 3 | 2 | 100%
| Use Case Diagrams | 1 | 2 | 2 | 2 | 100%
| Gantt Chart | 1 | 1 | 2 | 1 | 100%
| Activity Workflow Diagrams | 2 | 2 | 3 | 2 | 100%
| Sequence Diagrams | 2 | 2 | 3 | 2 | 100%
| Class Component Diagram | 2 | 2 | 3 | 2 | 100%
| SRS Section 3 - 4 | 5 | 2 | 5 | 2 | 100%
| Risks and Countermeasure | 5 | 1 | 6 | 1 | 100%
| SRS Section 5-6 | 6 | 3 | 8 | 3 | 100%
| Update of Diagrams | 7 | 1 | 7 | 1 | 100%
| Gantt Chart Update | 8 | 1 | 8 | 1 | 100%
| Preparation of Powerpoint and Report | 9 | 1 | 10 | 1 | 100%
ASSIGNMENT 2
| Development of 'Add/Remove stock' | 12 | 2 | 12 | 2 | 100%
| Development of 'Edit and Search stock' | 12 | 2 | 12 | 2 | 100%
| Development of 'Summary Report' | 12 | 2 | 12 | 2 | 100%
| Update existing/ Add new diagrams | 12 | 2 | 13 | 2 | 100%
| Testing of 'Add/Remove stock' | 14 | 2 | 13 | 2 | 100%
| Completion of 'Summary Report' | 14 | 2 | 14 | 3 | 100%
| Integration of application & fine tuning 'Summary Report' | 16 | 2 | 17 | 1 | 100%
| SRS fine tuning | 16 | 2 | 18 | 2 | 100%
| Review of Diagrams | 16 | 1 | 18 | 1 | 100%